SECTION 160 - PRELIMINARIES – CONSTRUCTION (TASMANIA)

##This section cross-references Sections 176, 177, 199, 714 and 860.

If any of the above sections are relevant, they should be included in the specification.

If any of the above sections are not included in the specification, all references to those sections should be struck out, ensuring that the remaining text is still coherent.

##Section 176 must be included in the specification:

##The term Independent Reviewer should be amended to Superintendent or Independent Certifier as applicable to selected project delivery model.

This section covers the Project Specific, Standard Specification amendments and administration items relating to construction contracts and should be read in conjunction with Sections 176, 177 and 199.

160.00	GENERAL

##DRAFTING NOTE: The following clauses are project specific and can be amended or additional clauses can be added to meet the specific requirements of the contract works. The formatting of the clauses and tables should be maintained to ensure consistency of presentation across contracts. When an existing clause is deleted the title “Not Used” shall be used beside the number and the subsequent numbering shall not be changed to ensure that any cross referencing is maintained. Any new project specific clauses shall be inserted after Clause 160.16.

160.01		CONDITIONS OF CONTRACT

The Specification Section 160 must be read in conjunction with AS 4000-1997 General Conditions of Contract as amended (the Conditions of Contract).

160.02	MOBILISATION AND COMMENCEMENT OF WORK

160.02A  Contractor’s Management Plans:

The Contractor’s Management Plans must include the following, which shall be submitted to the Superintendent at least 10 days prior to the Contractor mobilising to Site:

(a)	Environmental Management Plan

(b)	Traffic Management Schemes and Traffic Management Plans

(c)	A list of 2 emergency contacts

(d)	Information required under Clause 160.88 Work Health and Safety Incident Reporting

(e)	##List any additional project requirements.

Satisfaction of the above requirement is a Mobilsation Precondition for the purposes of the Conditions of Contract.

160.02B  Stakeholder and Community Engagement Plan

The Contractor must prepare a Stakeholder and Community Engagement Plan (SCEP) which shall be submitted to the Superintendent at least 10 days prior to the Contractor commencing the WUC.

Satisfaction of the above requirement is a Commencement Precondition for the purposes of the Conditions of Contract.

Stakeholder Risk and Opportunities Workshop

No later than 7 days following award of contract and prior to commencement of the WUC, the Contractor shall schedule and hold a Stakeholder Risk and Opportunities Workshop (see clause 177.02 of Section 177) with the Principal, Superintendent, and Contractor’s Stakeholder Engagement Specialist.

Satisfaction of the above requirement is a Commencement Precondition for the purposes of the Conditions of Contract.

160.03 	NOT USED

160.04	NOT USED

160.05	CODES OF PRACTICE

The Standard Sections reference VicRoads Codes of Practice. The Department of State Growth has prepared a Tasmanian Supplement to the VicRoads Codes of Practice for Pavements and Surfacings that reflects Tasmanian conditions and required jurisdictional practices. These amendments mainly relate to design matters. The Contractor must inform itself of the requirements of these referenced Codes of Practice and the Tasmanian Supplement applicable to the Works.

160.06	SCOPE OF WORKS

Scope of Works:

The Contract involves the following works:

##DRAFTING NOTE: Provide a description of the works required to be undertaken.

Limit of Contract:

Further to the Limits of Contract shown on the Drawings, the Limits of Contract includes those portions of the abutting properties sufficient for structures to be surveyed in accordance with Clause 160.82.

160.07	TRAFFIC MANAGEMENT

Standards and Guidance

The Contractor shall manage traffic in accordance with:

- The Tasmanian Traffic Act 1925;

- The Tasmanian Traffic (Road Rules) Regulations 1999;

- The latest version of the Traffic Control for Works on Roads, Tasmanian Guide;

- The latest version of AS 1742 Manual of Uniform Traffic Control Devices in particular Part 3; and

- The latest version of the Austroads Guide to Temporary Traffic Management (AGTTM) (Part 1 – 10).

Definitions specific to Traffic Management

Definitions are defined by the AGTTM Part 1: Introduction

‘AGTTM’ means the Austroads Guide to Temporary Traffic Management

‘Traffic Guidance Scheme’ means an arrangement of temporary traffic control devices to warn traffic and guide it around, through or past a worksite or temporary hazard

‘Traffic Management Plan’ means a document describing all essential traffic management matters associated with roadworks or works on roads. This includes risk assessment, traffic demand and accommodation, traffic routing and control and provision for vulnerable road users and special vehicles such as buses, trams or over-dimensional vehicles

Risk Control Measures

AGTTM Part 2: Traffic Management Planning, 2.3 Risk provides best practice guidance for the management of risk in temporary traffic management planning. Traffic is to be managed at a work site according to the hierarchy of control. This hierarchy is Austroads best practice, and the Contractor must reflect this in the Traffic Management Plan.

Hierarchy of Control

Traffic is to be managed at a worksite according to a hierarchy of control. This ‘around, through and past’ hierarchy of traffic management is Austroads best practice and must be reflected in a TMP. The Hierarchy of Control is available in AGTTM Part 2: Traffic Management Planning

Traffic Management Plan

Traffic Management for all worksites required in the performance of the works shall include preparation of a Traffic Management Plan.

The Traffic Management Plan must be written in accordance with the current version of AGTTM Part 2: Traffic Management Planning (available via Austroads) and AS1742.3.

Traffic Guidance Schemes

Where any change to existing traffic arrangements is proposed or where construction conflicts with normal traffic movements, the Contractor shall prepare a Traffic Guidance Scheme is accordance with the AGTTM and AS1742.3. Traffic Guidance Schemes shall include layout sketches for individual construction stages.

Implementation of Traffic Management Plan

The Contractor shall monitor the continued effectiveness of the Traffic Management Plan during the Contract and shall revise and update the Plan where necessary.

Traffic Management Plans are not required to be approved by the State road authority (a departure from AGTTM Part 2, Sections 2.6.4 and 4.14)

Implementation of Traffic Guidance Scheme

The Contractor shall implement only those traffic guidance arrangements as submitted to the Superintendent.

Should it be necessary to depart from a Traffic Guidance Scheme arrangement an amended Traffic Guidance Scheme shall be prepared.

On a daily basis, the Contractor shall ensure that all applicable traffic redirection and/or traffic management signs and devices are implemented prior to proceeding with any relevant WUC.

The Contractor shall monitor the effectiveness of the Traffic Guidance Scheme and revise it in response to incidents and/or traffic disruptions.

##DRAFTING NOTE: Use either alternative 1 or 2 below. Alternative 1 shall be used for all works where traffic volumes are below 3,000 vpd except for works on Category 1 roads or on the National Highway where Alternative 2 should be used. The clauses may be amended to suit project specific requirements. The unused alternative is to be deleted.

Delays to traffic

The stopping of traffic is only allowed for “long term” worksites and bituminous surfacing operations where works cannot occur under traffic.

Where there has been no advance warning, the stoppage time shall not exceed 8 minutes and where advance warning has been provided, the stoppage time shall not exceed 15 minutes.

The stoppage time shall be measured from the time at which the first vehicle is stationary and in total, the delay to traffic including queueing time and travel time through the worksite must not exceed twice the stoppage time.

##Alternative 1## Traffic management General

This is not a “High Profile Site” with the traffic volume on this section of highway approximately ### vehicles per day (AADT – two way) with ## heavy vehicles.

Traffic Management Plans shall as a minimum allow for the following:

- One lane of traffic no less than 3.0m in width during working hours;

- Two lanes of traffic outside of working hours;

- The length of activity interfering with traffic not greater than 500m (measured from the first worksite advance warning sign displayed to approaching road users to the final worksite sign on departure);

- No section of road trafficked under gravel greater than 1km in length with gravel sections separated by no less than a 1km of sealed road; &

- Ensure access to local connecting roads is maintained at all times.

##Alternative 2## Traffic management General

The site or part of the site is to be considered a High Profile site being where Annual Average Daily Traffic is equal to or greater than 3,000 vpd (sum of two directions).

For these sites the Traffic Management Plan shall also include the following:

- Identification by name and contact number for the person who shall be on site at all times during work with responsibility for implementing the traffic management. In areas outside mobile phone range other communication systems shall be provided to communicate back to the Contractor’s Operations Management base.

- Provide for addressing any special needs for local landowners and businesses and the nature and timing of personal contact to advise of the effects of traffic management.

- Co-ordination of works with adjacent work by other contractors (including, but not only; road, commercial building, agricultural and service/utility contractors) or Government Authorities.

- The nature of actions to cover the contingency where procedures do not achieve the requirements of this Specification.

Traffic Management Plans shall as a minimum allow for the following:

- Two lanes of traffic shall be open at all times;

- Maintain an 80 km/h speed limit through the site during working hours and after working hours except for:

    - No more than #1/2# sections of road of no greater than #2km# in length separated by no less than a #2km# section of road at 80 km/h speed limit;

- Ensure access to local connecting roads is maintained at all times.

Roadwork Speed Limit Spray Sealing Works

Sprayed sealing or other activity requiring works to occur without temporary safety barrier, thus requiring a lower speed limit, is restricted to a maximum length of 2km.

The speed limits following spray sealing must be maintained as detailed in the schedule below.

| Period following Sealing | Speed Limit | Requirements |
| --- | --- | --- |
| First 24 Hours | 40 km/h | The surface shall be suction swept prior to opening to traffic. The depth of loose aggregate build-up along the edge of traffic lane shall not exceed 20mm. |
| From 24 to 48 Hours | 60 km/h | Ensure adequate rolling to retain aggregate and regular sweeping to remove loose aggregate. |
| From 48 Hours | 80 km/h | Complete line marking and increase speed limit to 80 km/h. |

Temporary Pavement Markings

All temporary pavement marking shall be the same colour over the entire length of the site.

All redundant line marking and Raised Reflective Pavement Markers (RRPMs) within the limits of work shall be removed or covered so that they are not visible to road users under all conditions, including dark and wet conditions.

There is to be no evidence of temporary pavement markings on the final surfacing.

Property Accesses

Unless otherwise agreed in writing with the property occupier, both pedestrian and vehicular access to adjacent properties shall be maintained at all times.

Where an access has been identified for permanent closure, the Contractor shall advise the relevant landowner in writing not less than two (2) weeks prior to closing the access.

Over Size-Over Mass Vehicles

The Contractor must recognise the ongoing and legitimate need to reasonably accommodate Over Size-Over Mass vehicles travelling through the site. The Contractor will provide the Superintendent with contact details for the site supervisor with the authority to reach agreements with operators and facilitate travel through the site where appropriate. The contractor must not unreasonably withhold a request to travel through the site.

Information about agreements is to be provided to the Superintendent prior to the time of travel. The authorised site supervisor contact details will be made available by the Department to Over Size-Over Mass operators.

Prior to travel through any State road work site, where the vehicle inclusive of load exceeds 3.5 metres in width, the Over Size-Over Mass vehicle operator is required to make direct contact with the Construction Contractor to agree travel arrangements and conditions and to ensure that the vehicle, together with its load, can safely negotiate the site without unreasonably disrupting other road users or causing damage.

Where a Transport Escort is involved in the activity, written confirmation of the agreement between the operator and the authorised site supervisor must be made available (?by the Construction Contractor OR the operator?) and agreed with the Transport Escort prior to travel.

Roadworks Roundup

The Principal maintains a Roadworks Roundup published on the Transport Services website every Friday afternoon that advises the community of scheduled works taking place on the State road network over a two-week period – see https://www.transport.tas.gov.au/roadworks/roadworks_map

The works entered into the Roadworks Roundup need to adhere to specific timeframes, with the length of those timeframes dependent on the potential traffic impacts and whether the road in question is a Group A or B major commuting route, as defined under the Major Commuting Routes Policy:

https://www.transport.tas.gov.au/roadworks/roadworks_map/restrictions_on_major_commuting_routes

The Contractor must submit to the Principal details of new works or amendments to existing works that require traffic management by 4:00pm Wednesday of every week (submission day) such that the works can be included in the Roadworks Roundup that will be published the following Friday.

The Contractor shall not commence work where the traffic management details have not been submitted to the Principal and where scheduled to commence according to the following.

Prior to 9 days following the submission day for works:

- involving lane closures on a Group A or B road under the major commuting routes policy

- involving a full road closure on any road

- involving work on a Group A or B road outside of the normal allowed hours of work.

Prior to 7 days following submission day for works:

- on a Group A or B road that only require a reduced speed limit

- on any other roads (not Group A or Group B roads) that do not include a full road closure.

160.08	    NOT USED

160.09	 ENVIRONMENTAL MANAGEMENT

160.09A	Threatened Flora Exclusion Zones

The locations outlined in the Exclusion Zone Schedule contain Threatened flora species and shall be protected in accordance with Standard Specification Clause 176.I(c).

Threatened Flora Schedule

| Location | Details of Threatened Flora |
| --- | --- |
| ## Add details |  |

160.09B	Weed Management

Weeds have been recorded in the vicinity of the proposed works. A weed survey of the project footprint identified weed locations as outlined below.

Weed Schedule

| Location | Details of Weeds |
| --- | --- |
| ## Add details |  |

Weeds shall be treated in accordance with the requirements of Section 176.12.

160.09C	Threatened Fauna and Faunal Habitat

The details of threatened fauna and faunal habitat recorded in the vicinity of the proposed works are shown below.

Threatened Fauna Schedule

| Location | Description | Action Required |
| --- | --- | --- |
| ## Add details |  |  |

160.09D	Aboriginal and European Heritage

The details of Aboriginal and European Heritage sites recorded in the vicinity of the proposed works are shown in the schedule below.

Heritage Site Schedule

| Location | Description | Action Required |
| --- | --- | --- |
| ## Add details |  |  |

160.10	PROJECT INFORMATION SIGNS

Project Information Signs ##are required/ are not required##

Where required the Project Information Signs are to be placed at the following locations:

## DRAFTING NOTE:(the sign types/drawing numbers in the schedule below are applicable to State Government funded works only - in the case of Federal Government funded works contact State Roads Project Manager for information on project information signing requirements and insert details in the schedule below.

Sign Types for Federal Government funded works are detailed in Building Australia Signage Guidelines -https://investment.infrastructure.gov.au/sites/default/files/documents/buildaus-signage-guide_0224.pdf. d

Project Information Sign Schedule ##(type in the appropriate requirements below):

| Serial | Sign Type | Drawing No. | Number Required | Location |
| --- | --- | --- | --- | --- |
| (a) | Type X | XXX | ##: | ##: |
| (b) | Type X | XXX | ##: | ##: |
| ##: |  |  |  |  |

The Contractor shall supply, install, maintain and later remove project information signs as specified below:

(a)	Supply

The Contractor shall supply project information signs in accordance with the requirements of Section 860 - Manufacture of Road Signs and the Department’s relevant signage guidelines. Project information signs shall be regarded as a Category B Sign for the purposes of Section 860.

Project information signs identified as an Australian Government Sign Type in the Project Information Sign Schedule above (if any) shall be supplied in accordance with the Building Australia Signage Guidelines.

The design of the sign shall comply with the requirements of the Drawings specified in the Project Information Sign Schedule in Clause 160.10.

(b)  Mounting and Location

The Contractor shall mount the information signs on posts suitable for each location chosen in accordance with the Australian Standards and Department’s specification Section 714 – Sign Installation.

Project information signs identified as an Australian Government Sign Type in the Project Information Sign Schedule above (if any) shall be located, installed and mounted (as applicable) in accordance with the Building Australia Signage Guidelines, and installed prior to the commencement of the WUC.

(c)	Removal

Project information signs as identified as an Australian Government Sign Type in the Project Information Sign Schedule above, must be removed once construction works have been completed.

For all other project information signs, those signs shall remain in place for the entire defect liability period and be removed by the Contractor prior to the Superintendent issuing the Final Certificate, or as otherwise directed by the Superintendent.

The Building Australia Signage Guidelines are available at: https://investment.infrastructure.gov.au/sites/default/files/documents/BuildAus_SignageGuide_1123.pdf

160.11	VARIABLE MESSAGE SIGNS

Variable Message Signs ##are required/ are not required##

##DRAFTING NOTE: Where VMS’s are required complete the following as applicable. Note the location is optional.

The Contractor shall provide #No Variable Message Signs.

The Variable Message Signs are to be located as follows:

- ##insert location

Variable Message Signs are to be installed in accordance with the requirements of the Stakeholder and Community Engagement Plan produced in accordance with Specification Section 177.

160.12	SERVICES

160.12A 	EXISTING SERVICES

The Works are in close proximity to the following known services: ##DRAFTING NOTE: Amend schedule below for known services

| Service Owner | Details and Location | Agreement Details |
| --- | --- | --- |
| ##Amend list below as required | ## Add details | ## Add details |
| Tas Networks Pty Ltd |  |  |
| Telstra Corporation |  |  |
| Optus Ltd |  |  |
| NBN Co |  |  |
| Tas Water Pty Ltd |  |  |
| Tas Gas Pty Ltd |  |  |
| Traffic Signals Maintenance (Traffic.sig@stategrowth.tas.gov.au) |  |  |

Before commencement of the Works the Contractor shall convene a meeting with the relevant Service Owner to determine the programming necessary for coordination of the work of the Contractor with that of the Service Owner.

160.12B	PROVING SERVICES

Prior to commencing works, the Contractor shall make appropriate enquiries to confirm the location of all services and service authority assets.

HP	Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.

The Contractor shall construct the works so as not to interfere with or impact on any service infrastructure. However, if in proving the services it becomes apparent that the Works cannot proceed as designed, the Contractor shall immediately advise the Superintendent.

160.12C	PRIVATE SERVICE CONNECTIONS

Where Private Service Connections are impacted by the works, the Contractor shall be responsible for liaising with the service connection owner in regard to any interruption or service re-instatement.

160.13	UNSUITABLE MATERIALS

##DRAFTING NOTE: It is essential that the designer undertakes a risk assessment to determine the location and quantity of Unsuitable Material and includes this information on the Drawings.

Further to Standard Specification Clause 204.07 locations and volumes of unsuitable materials are shown on the drawings.

For all unsuitable materials replaced the Contractor shall record the quantity.

160.14	SPRAY BITUMINIOUS SURFACING TREATMENTS

160.14A	SPRAYED BITUMINIOUS SURFACING SELECTION

##DRAFTING NOTE: This clause is not to be removed

The following is added to Clause 408.11(a).

When selecting binder types in accordance with the requirements of Part 4K- Selection and Design of Sprayed Seals the temperature environment used for selection is deemed to be as follows:

- Cool for initial seals in accordance with Table 4.6

- Low for other seals in accordance with table 4.7

160.14B	CONTRACTOR SELECTION OF SPRAYED BITUMINIOUS TREATMENT

##DRAFTING NOTE: The following section shall be used where the Sprayed Bituminous  treatments are to be selected by the Contractor as part of the works to be undertaken. Also note that Table 408.171 will still need to be populated with information such as locations and Traffic Data but no seal information is to be provided. Drawings are only to specify the location of the seal treatment.

The Contractor is to select all Spray Bituminous surfacing treatment for the works including both the initial and secondary treatments.

Further to section 408 the treatment shall be selected in accordance Austroads Guide to pavement Technology Part 4K- Selection and Design of Sprayed Seals.

The secondary treatment is to be applied over the area shown on the drawings or specified elsewhere in the Contract and incorporate a minimum 10mm size aggregate. The secondary treatment shall use aggregates with a minimum PSV stated in the Bituminous Surfacing Requirements Schedule.

Any initial treatment which is intendent to be trafficked for more than 6 months shall use aggregates with a minimum PSV of 48.

160.15	Polished Stone Value (PSV) Requirements

The following minimum PSV values apply for the following bituminous surfacing products and locations:

Bituminous Surfacing Requirements Schedule

| Bituminous Surfacing | Location | PSV Value |
| --- | --- | --- |
| ## Add details |  |  |

The following is added to Clause 407.03(g).

Notwithstanding the other requirements of this clause where a minimum Polished Stone Value (PSV) is specified for asphalt wearing courses all individual components of the Coarse Aggregate shall meet the minimum specified Polished Stone Value.

160.16	RIDE QUALITY FOR PAVEMENTS CONSTRUCTED UNDER TRAFFIC

##DRAFTING NOTE: The following clause is to be included where it is expected that some or all of the pavement is to be constructed under traffic e.g. overlays on existing roads, tie-ins at the ends of new construction.

Where pavements have been constructed under traffic the Superintendent shall add an additional 0.2 IRI to the Maximum Mean Lane Roughness value in Table 180.102- Standard of Ride Quality for the part of the works that is constructed under traffic. For the purpose of applying this clause “pavements constructed under traffic” are deemed to be in areas where traffic is applied to the pavement during all stages of the construction and cannot be diverted during construction. This does not apply to works where the construction is substantially undertaken clear of traffic and the Contractor chooses to divert traffic onto the new pavement for short periods of time.

160.40	AMENDMENTS TO STANDARD SECTIONS

##DRAFTING NOTE: The following clauses are amendments to the Standard Specifications Sections and can be included or deleted as required. No changes to the wording of these amendments are to be made, or new amendments added, unless approved by State Growth as a Departure from Standard. When an existing clause is deleted the title “Not Used” shall be used beside the number and the subsequent numbering shall not be changed to ensure that any cross referencing is maintained.

160.41	INSPECTION OF SIGNS

Further to the requirements of Clause 714.04 CONFORMITY WITH DRAWINGS, the Contractor must make the sign available for inspection by the Superintendent and Principal including by providing a photo of the sign to the Superintendent and Principal.

HP         The sign must not be erected, installed or otherwise made visible to the public until the Superintendent has directed that it may be installed.

160.42	NOT USED

160.43	SITE EXCAVATION

Clause 204.07(b) is amended by deleting the last paragraph commencing with “Where material” and the sub clauses (i), (ii) and (iii).

160.44	SHOULDER SEALING AND MINOR WIDENING WORKS

##DRAFTING NOTE: The following Clauses 160.44Aand 160.44B shall be used for Shoulder Sealing or other minor widening works (such as minor curve widenings) where excavations are required to be back filled on the day of excavation. These clauses are not to be used where there is extensive pavement widening such as the addition of adjacent lanes.

160.44A	SITE EXCAVATION

The following Clause shall replace Clause 204.6(e)

The material at the Cut Floor Level shall have a CBR of not less than that specified for Type B material. The CBR can be measured using either of the following methods:

- Soaked CBR in accordance with VicRoads Code of Practice RC 500.20

- In-situ field assessment using a Farnell Penetrometer in accordance with the State Growth procedure

- In-situ field assessment using a Dynamic Cone Penetrometer in accordance with AS 1289.6.3.2 and the State Growth procedure.

Where the In-situ methods in (ii) and (iii) above are used testing shall be undertaken at a rate of 1 for every 200m2 of subgrade.

In-situ material below the Cut Floor Level having a CBR less than that specified for Type B material shall be removed to a depth shown on the drawings or as directed by the Superintendent. The material shall be replaced with conforming Type B material.

Where removal and replacement of material is not required the cut floor level will not require any additional treatment.

160.44B	PAVEMENT COMPACTION

The following amendments are made to Specification 304.

The Scale for Assessment of Compaction specified in Table 304.121 shall be Scale B.

Further to Clause 304.06 the Contractor may elect to construct the Lower and Upper Sub-Base layers using the same material specified for the Upper Sub-Base layer. The combined Sub-Base layers shall be tested as a single layer to a minimum depth of 300mm.

Further to Clause 304.08(b)(iv) test rolling of the Sub-Base layers may be omitted on narrow areas of widening where it cannot be practically undertaken. Test rolling of the Base layer is still required.

160.45     NOT USED

160.46	NOT USED

160.47	BRIDGE NUMBER, LOAD CAPACITY AND DATE MARKS

The following is added to Section 610.

The Contractor shall provide the necessary stencils for placement on the face of formwork to show clearly on the finished concrete, the bridge number, the design loading and year of construction. The stencil lettering shall be 75mm high, 5mm deep and be clearly legible.

The depth of the lettering shall not reduce the minimum cover to the reinforcement below that specified. The lettering shall be mirror checked prior to placement of concrete.

For bridges, culverts, pedestrian and stock underpasses, the asset number; design loading and the year of construction shall be marked into the inside face of the left hand kerb at Abutment A (Abutment A is the abutment listed on the lower link map reference chainage) and on the diagonal kerb face at the other abutment unless otherwise approved by the Superintendent.

160.48	FENCING (W-BEAM SAFETY BARRIER)

The following is added to Clause 708.07(b)

New W-beam safety barrier shall be supplied as 4-metre lengths.

The following is added to Clause 708.07(c).

All road safety barrier terminals shall be redirective non-gating terminals and shall be installed in accordance with the manufacturer’s recommendations.

160.49	PERMEABILITY TESTING

The following is added to Section 812.

Permeability testing shall be carried out for Class 1 and Class 4 crushed rock. The test results shall be supplied to the Superintendent along with other pavement test results. Notwithstanding the specification, material that does not meet the permeability requirements can still be used as Class 1 and class 4 material.

160.50	ADMINISTRATION

##DRAFTING NOTE: The following clauses are related to the administration of the contract. No changes to the wording of these amendments are to be made unless approved by State Growth as a Departure from Standard.

160.51	QUALITY MANAGEMENT SYSTEMS STANDARDS

The Works under this Contract shall be undertaken in accordance with a Quality Management System that meets the requirements of relevant AS/NZS ISO Standards.  The Standards specified in this clause form part of this Specification.  Copies are not included in this document.

These Standards include:

AS/NZS ISO 9001	Quality Management Systems – Requirements

AS/NZS ISO 14001	Environmental Management Systems – Specification with guidance for use

AS/NZS 4801	OHS – Management Systems

The Quality Systems shall demonstrate compliance with all relevant Acts and Regulations and the requirements of the Contract Specification and as a minimum must include:

•	a Quality Plan which addresses the requirements in this Specification and demonstrates compliance with relevant AS/NZS ISO Standards;

•	Templates for Inspection and Test Plans and templates for all Lot Records required by Inspection and Test Plans;

•	Commissioning Plans required by the Contract;

•	Construction Procedures required by relevant specifications;

•	Procedures and systems for management of design and construction records.

The contractor must exercise quality control of the Works, including works undertaken by sub-contractors, and must establish systems and procedures that will provide the information specified in this section to provide assurance of that control.

160.52	QUALITY TERMS AND DEFINITIONS

Quality terms and definitions shall be as defined by the Australian Standard AS/NZS ISO 9000 Quality management systems – Fundamentals and vocabulary.

Other definition and terms shall be as follows:

‘asset component’ means a component part of a road, bridge or other asset forming part of the works.

‘accredited laboratory’ or ‘accredited method’ means –

- for all inspections (other than for material which is supplied from outside Australia) a laboratory or method (as the case requires) accredited by the National Association of Testing Authorities (NATA) for those inspections or inspection methods;

(ii)	for all material which is supplied from outside Australia, a laboratory or method accredited by NATA for those inspections or inspection methods or by another laboratory or method accredited by a recognised certifying body approved in the Contract or, if the Contract does not provide such approval, then by a recognised certifying body approved by the Superintendent.

‘Independent Reviewer’ means the independent reviewer appointed by the Superintendent to undertake audits of the Quality Management System.

‘inspection’ means and incorporates measuring, testing or otherwise examining goods and services or works or materials (including, where appropriate, raw materials, components and intermediate assemblies) for determining conformity with the specified requirements.

‘lot’ (or ‘work lot’) means a discrete element of work which has been constructed in a continuous operation under essentially uniform conditions and is essentially homogeneous with respect to material properties, general appearance and construction process. A lot must only comprise a single layer, batch or area of like work and unless otherwise specified the extent of each lot must not exceed one day’s production.

‘lot Diagram’ means a diagram showing the location and bounds of each Work Lot within an Asset Component comprising multiple lots that are not identified separately on the design drawings or in the Work Breakdown Structure. (e.g. an earthworks embankment, a section of pavement, or a soil nail wall).

‘lot Records’ means all test and inspection records and certificates required by the applicable Inspection and Test Plan.

‘lot Register’ means a register or system that enables identification of each lot within the Work Breakdown Structure and the completion and conformance status of each lot.

‘measuring’ includes checking for line, level, dimensional accuracy and quantity.

‘on-line access’ means accessible via the internet as an electronic record.

‘test’ includes taking of samples and specimens and preparation of materials and work for testing.

‘Hold Point ‘means those points beyond which the stated activity must not proceed without the Quality Assurance Verifier’s approval to proceed.  The Quality Assurance Verifier’s approval to proceed beyond the Hold Point does not relieve the Contractor of responsibility for satisfactory execution or performance of the work.

Hold Points are identified in the specification by the letters HP in the left margin and by bold text print or arise from a nonconformity.

Text which is bold typed but not identified by the letters HP in the left margin does not reflect a Hold Point.  Such text reflects specified obligations on the Contractor requiring the review or approval of the Quality Assurance Verifier.  They are bold typed for ease of identification.

‘Quality Assurance Verifier’ – a person engaged by a contractor to undertake specified quality assurance functions as identified in this specification, including release of Hold Points.

‘Review Point’ – Verification check points identified in the Inspection and Test Plans requiring verification of requirements and collection of records.

‘Witness Point’ - Verification check points identified in the Inspection and Test Plans that are not designated as Hold Points but require inspection by the Superintendent.

‘work package’ – one or more lots of the same work kind covered by a single Inspection and Test Plan.

160.53	QUALITY REPRESENTATIVES

The Contractor shall appoint persons to the following Quality Representative positions:

•	a Quality Management Representative to manage and administer the Contractor's Quality Management System in accordance with the appropriate Australian Standard(s) and the Contractor’s Quality Plan; and,

•	one or more Quality Assurance Verifiers to manage and administer the releasing of Hold Points, the closure of Work Packages and the closure of Notices of non-conformance relating to Work Lots. The Quality Assurance Verifiers, must:

be accountable to the Contractor, but required to act as independent verifiers of the quality assurance process;

not be involved in the day-to-day construction or supervision of construction;

have appropriate qualifications, experience and competence to undertake their role proficiently;

have a thorough understanding of relevant design documentation and specification requirements;

be the only persons authorised to release Hold Points and close Work Packages within their designated scope of authority;

The Quality Assurance Verifier is to meet the following requirements:

- For road construction works a minimum of 5 years’ experience in design or construction of roadworks in particular earthworks, pavements and sealing.

- For bridge construction works an Engineer eligible for membership of Engineers Australia and a minimum of 8 years’ experience in design or construction of bridges.

- For bridge rehabilitation works in addition to the requirements for bridge construction above where the works require preparation or repairs to concrete or steel structures experience in major structure rehabilitation is also required.

- Experience in the implementation of quality assurance systems.

The following Hold and Witness Points are to remain with the Superintendent all other Hold Points are to be undertaken by the Quality Assurance Verifier:

##DRAFTING NOTE: Consideration needs to be given to any project specific hold or witness points as to whether they need to be allocated to the Superintendent or Quality Assurance Verifier. Any Hold points allocated to the Superintendent must be added to the table below.

| Specification Clause | Description |
| --- | --- |
| 160.07 | Traffic Management |
| 160.41 | Inspection of Signs |
| 160.85A | Wording on VMB’s |
| 204.04 | Materials |
| 204.06 | Site Excavation |
| 204.07 | Unsuitable Materials |
| 204.09 | Approval of Borrow Excavation in Road Reserve |
| 205.04 | Use of Oversize Rock |
| 408.13 | Treatment of Seal Defects |
| 430.10 | Treatment of Defects |
| 431.12 | Treatment of Defects |
| 605.12 | Treatment of Defective Piles |
| 610.07 | Approval of Concrete Mix Design |
| 610.24 | Repairs of Cracked Concrete |
| 611.05 | Use of Reinforcing Steel not covered by Third Party (ACRS) certification |
| 630.07 | Use of Weld Repaired Steel |
| 680.05 | Use of Alternative Anchor |
| 680.10 | Rectification proposals for failed anchors |
| 683.14 | Rectification proposals for failed anchors |
| 688.09 | Approval of Repair Procedure |
| 689.08 | Deviation from manufactures repair specifications |
| 701.25 | Approval of Repair procedures |
| 721.A12 | Approval of removal of unsuitable pavement marking |
| 765.03 & 04 | Changes to approved design details |
| 801.03 | Use of non-compliant materials with proven record |
|  | Any other Hold Point or Specification requirement not listed above which requires approval or rectification of non-compliant product |

Any proposed changes to the nominated Quality Representatives must be notified promptly to the Principal and the Superintendent. Within 10 working days of receipt of the notice of nomination of Quality Representatives, the Superintendent shall issue advice of acceptance or rejection of the nominations.

160.54	QUALITY PLANS AND PROCEDURES

(a)	General

The Contractor shall submit for consideration by the Superintendent a controlled copy of the quality plans and procedures relating to each stage of the WUC not less than 10 Business Days prior to the commencement of that stage of the work unless specified otherwise.

The quality plans and procedures required under the Contract shall cover but not be limited to the following management systems:

•	Quality

•	Traffic

•	Environmental

•	Work Health and Safety

•	Incident Management and Reporting.

The Quality Plan must:

•	Nominate and define the responsibility, authority and reporting function of personnel primarily responsible for ensuring the effectiveness of the Quality Management System, including:

a Quality Management Representative who has responsibility for ensuring that the requirements of the Quality Plan are implemented and maintained, and for authorising closure of Notices of non-conformance that are not related to Work Lots; and

one or more Quality Assurance Verifiers responsible for releasing Hold Points, authorising closure of Work Packages and authorising closure of Notices of non-conformance relating to Work Lots,

•	Designate for each Quality Assurance Verifier the scope of construction activities that they are authorised to verify; and,

•	Provide for all Quality Representatives sufficient information to demonstrate relevant qualifications, experience and required competencies to exercise the designated scope of their authority.

A quality plan or procedure shall be changed if it:

(i)	does not adequately address the specification requirements;

(ii)	is causing non-conformity;

(iii)	has to be changed because of an audit; or

(iv)	no longer represents current or appropriate practice.

The Contractor shall immediately notify the Superintendent of any change to the plans or procedures and the amended documentation shall be submitted to the Superintendent within 5 Business Days of such notice.

(b)	Management System Plans

The quality plan for a stage of the contract shall require the preparation of the following management system plans and shall be forwarded to the Superintendent by the nominated time:

•	Traffic Management Plan [refer Section 160.07]

•	Environmental Management Plan [refer Section 176:]

•	Work Health and Safety Management Plan [refer clause 11B.2 of the Conditions of Contract].

(c)	Work undertaken by subcontractors

The Contractor must ensure that all works carried out by subcontractors complies with the requirements of this Specification.

The Quality Plan must include:

•	procedures and criteria for the evaluation, selection, supervision and monitoring of performance of subcontractors;

•	procedures that will ensure that subcontractors comply with the Quality Plan requirements relating to:

the Work Breakdown Structure;

Inspection and Test Plans;

Hold Points and Witness Points;

Product identification and traceability;

Construction procedures;

Control of non-conformance;

Progressive closure of Work Packages;

Management of Defects

On-line access to records

160.55	WORK BREAKDOWN STRUCTURE

The Work Breakdown Structure:

•	Must be subdivided into discrete sections of the Works between readily identified points such as intersections, interchanges, cross roads, stream crossings, or other points established by the Contractor to manage staging of the Works;

•	Within each discrete section, must be structured in successive layers of:

Assets, classified by standard Asset Types;

Asset Components within each Asset, classified by standard Component Types; and

Work Packages within each Asset Component, where each Work Package represents a group of Work Lots covered by an Inspection and Test Plan

•	Must include a system of uniquely identifying each separate element within the structure

•	Must be progressively defined and maintained in the contractor’s record management system.

Unless otherwise specified, the standard Asset Types and Asset Component Types must conform to the Austroads Guide to Project Delivery Part 5: Road Construction Quality Assurance.

The Quality Plan must include the following details for the Work Breakdown Structure:

•	A definition of the discrete sections of the Works.

•	The standard Asset Types and Asset Component Types.

•	A system that will be used to uniquely and consistently identify each element of the Work Breakdown Structure in the Design and Construction Program, Design Documentation, and Construction Records.

160.56	INSPECTION AND TEST PLANS

The content of the Inspection and Test Plans and associated lot records must conform to the Austroads Guide to Project Delivery Part 5: Road Construction Quality Assurance.

The Contractor must:

•	ensure that Inspection and Test Plans include all verification check points required by relevant specifications;

•	prepare a template for each of the Construction Records designated in each Inspection and Test Plan; and,

•	submit each Inspection and Test Plan template and the associated Construction Record templates at least 10 Work Days prior to commencing any related construction activities.

Verification check points identified in the content of the Inspection and Test Plans shall be designated as either a Review Point, Hold Point or Witness Point.

Construction Record templates must show the specified inspection and test requirements and acceptance criteria, and require entry of the actual inspections and tests performed and test results.

The submitted templates must be amended to address any non-conformances notified by the Superintendent.

Prior to commencing any Work Package, an Inspection and Test Plan and associated Construction Record must be prepared using the relevant template.

The Superintendent may review the Inspection and Test Plans and may elect to nominate one or more Hold Points as Witness Points or as Superintendent-released Hold Points in addition to those in Clause 160.53.

160.57	NOMINATED HOLD POINTS AND WITNESS POINTS

The Contractor’s quality plans and procedures shall identify all Hold Points and Witness Points including all Hold Points identified by the Specification.

The Superintendent must be given reasonable notice of each Witness Points and the intended release of each Hold Point and may nominate persons to attend each Witness Point and the release of each Hold Point. Unless otherwise specified or agreed by the Superintendent, reasonable notice means at least 2 Business Day.

A Hold Point must only be released by the nominated Quality Assurance Verifier, who must physically inspect the works and the completed Lot Records to verify compliance with the Inspection and Test Plan and the Design Documentation before releasing the Hold Point.

160.58	PRODUCT IDENTIFICATION AND TRACEABILITY

The Contractor’s procedures and systems for records management must ensure that:

•	every Work Lot required to construct the Works is uniquely identified;

•	each Work Lot is recorded on the Inspection and Test Plan for the relevant Work Package within the Work Breakdown Structure;

•	the Lot Records for each Work Lot are traceable to the Work Lot and to the relevant checkpoint within the applicable Inspection and Test Plan; and,

•	all requisitions for testing and the corresponding test certificates are traceable to the relevant Lot Record.

160.59	CONSTRUCTION PROCEDURES

The Contractor must ensure that documented construction procedures:

•	will achieve specified requirements;

•	are understood and used by construction personnel;

•	identify Hold Points and Witness Points that must be notified to the Superintendent; and,

•	are reviewed for corrective action in the event of non-conformance.

Construction procedures that are required under the Contract to be submitted for review:

•	must be identified in a schedule in the Quality Plan which shows the proposed date for submission;

•	must be submitted to the Superintendent at least 10 Business days prior to the planned commencement of the respective construction activities; and,

•	must be amended to address non-conformances notified by the Superintendent before the construction activities commence.

160.60	CONTROL OF NON-CONFORMING PRODUCT

The Contractor must;

•	notify the Principal and the Superintendent of any non-conformance with respect to the contract requirements within 2 Business Days of the non-conformance being identified by the Contractor or notified by the Principal or the Superintendent;

•	maintain a register in which each Notice of Non-Conformance and the status of each Notice is recorded;

•	review and analyse the cause of all non-conformances and develop a plan of corrective action to minimise the likelihood of re-occurrence.

The Quality Plan must include a procedure for managing non-conformances and identify which of the following options is proposed:

•	rectification to achieve full compliance, thereby extinguishing the non-conformance;

•	a Design Change, to accommodate the non-conformance whilst still meeting all specified requirements;

•	repairs permitted by the relevant Reference Documents, subject to the Principal accepting proposed repair procedures and Inspection and Test Plans;

•	the Principal accepting the non-conformance as a Defect.

A Work Lot non-conformance must be treated as a Hold Point which must not be released until:

•	a procedure for managing non-conformances acceptable to the Principal is submitted to the Principal and the Superintendent;

•	the Superintendent has been notified of the intended release of the Hold Point;

•	the works and the lot records have been inspected to verify that the accepted procedure for managing non-conformances has been implemented; or

•	any Work Lot non-conformance accepted by the Principal as a Defect has been recorded in the Defect register; and

Each Notice of Non-Conformance must be recorded in the register as either a Work Lot non-conformance or a process non-conformance, and the status of each Notice of Non-Conformance must be recorded as ‘Open’ in the register until;

•	in the case of process non-conformances, closure has been authorised by the Quality Manager; or

•	in the case of Work Lot non-conformances, the associated Hold Point has been released.

The register must enable each Work Lot non-conformance to be traced to the affected Work Package in the Work Breakdown Structure.

160.61	PROGRESSIVE CLOSURE OF WORK LOTS

The Quality Plan must include procedures that will ensure that Work Packages are closed as soon as practicable after completion of the Work Lots within the Work Package.

Work Packages must not be closed until:

•	all related inspections have been completed;

•	all tests have been completed and the results recorded;

•	all non-conformances have been notified and recorded in the register of Notices of non-conformance;

•	all non-conformances have either been closed or with the Superintendent's approval, transferred to the Defects List;

•	all changes to design details have been recorded and cross referenced to the relevant Design Change Notice on a marked up and certified copy of the relevant drawings;

•	the complete set of Construction Records are available for inspection by the Principal and the Superintendent via the on-line access service;

•	the designated Quality Assurance Verifier authorises closure of the Inspection and Test Plan to which the Work Lots relate; and,

•	closure of the Work Package is recorded in the Contractor’s records management system.

Work Packages must be closed before:

•	The Work Package is covered up, unless approved otherwise by the Superintendent;

•	Manufactured components, including precast and fabricated components, are erected or installed into the Works;

•	The Work Package can be recorded as completed on a Progress Certificate.

160.62	DEFECTS

Prior to completion of the Works and for the duration of the Defects Liability Period the Contractor must maintain a register for monitoring the rectification of any Defects:

•	recorded in the process of closure of Work Packages; or

•	identified by the Contractor or notified by the Principal or Superintendent after closure of the respective Work Packages.

Records of Defects must not be deleted from the Defects Register.

The Defects Register must:

•	identify the Asset Component to which the Defect relates;

•	include sufficient detail to enable the Defect to be readily located;

•	identify any Defects proposed to be accepted by the Principal and include references to any correspondence between the parties in respect of such Defects;

•	show details of the proposed rectification plan;

•	record when the Defect is rectified and when the Defect is closed.

A Defect must not be closed in the Defects Register unless:

•	the rectification plan has been accepted in writing by the Principal;

•	a nominated Quality Assurance Verifier has physically inspected the rectification works and verified compliance with the rectification plan; and

•	a nominated Quality Assurance Verifier has authorised closure of the Defect; or

•	the Defect has been accepted in writing by the Superintendent.

160.63	AUDITS BY THE CONTRACTOR

The Contractor shall carry out audits in accordance with the requirements of AS/NZS ISO 19011:2002 ‘Guidelines for quality and/or environmental management systems auditing’.

The Contractor shall prepare an audit and surveillance schedule for each subcontractor, which shall be submitted to the Superintendent for review prior to the commencement of work by the subcontractor.  The Contractor shall conduct regular surveillance and audits of all on-site and off-site subcontractors, sufficient to ensure that all work and materials comply with the Contract.

The Contractor shall notify the Superintendent of the times when formal audits of a subcontractor are to occur.

The Contractor shall carry out surveillance for precast concrete, structural steelwork and protective coatings of structural steelwork in accordance with the following references:

VicRoads Technical Bulletin No 46 - Guide to Surveillance of Structural Steelwork

VicRoads Technical Bulletin No 47 - Guide to Surveillance of Precast Concrete

VicRoads Technical Bulletin No 48 - Guide to Surveillance of Protective Coatings of Structural Steelwork.

The Contractor shall comply with all the requirements of these references including using companies accredited by NATA for surveillance of these respective activities and surveillance officers engaged by these companies having the qualifications and experience specified in these respective references.

160.64	RECORDS

During the execution of WUC, the Contractor shall maintain records pertaining to the Contract in accordance with the Contract and the Contractor’s Quality System.

The Contractor shall maintain the following records as a minimum:

- all test records;

- all Hold Points;

- all Inspection and Test Plans;

- all relevant survey information;

- all plant and labour records confirming daily usage and work activities throughout the Contract;

- all weather records; and,

- copies of all construction Programs.

The Contractor must establish records management procedures and systems that will ensure that:

- the construction records identified in the left column of table below, including records for works undertaken by subcontractors, are integrated within a system managed by the Contractor;

- the Principal and the Superintendent have convenient on-line access (electronic documents accessible via the internet) to the design and construction records; and.

- design and construction records are recorded progressively and promptly in the system to show, as far as reasonably practicable, the current status of the Works.

Construction Records

| Design & Construction Records | Reporting Variables |
| --- | --- |
| The Work Breakdown Structure | Project Section or Asset Type |
| Construction Procedures |  |
| ITP & Work Lot Record Templates |  |
| Work Lot register | Work Breakdown Structure or Status |
| Closed Work Lot Records | Work Breakdown Structure |
| Sampling and test results register | Work Lot or Test Laboratory |
| As-Built drawings | Work Breakdown Structure |
| Notice of non-conformance register | Work Breakdown Structure |
| Defects register | Work Breakdown Structure |

The Contractor shall make all records pertaining to the Contract available to the Superintendent at all times and when requested by the Superintendent, the Contractor shall provide a copy of the requested records within 5 Business Days.

The on-line access must:

•	present records in a format acceptable to the Principal and the Superintendent.

•	enable convenient searching and selection of records.

•	enable printing of reports or downloading of reports in electronic (Microsoft Office or Adobe PDF) format.

• 	all current and superseded versions of documents must be accessible at all times with the current version being predominant and each superseded version clearly distinguishable from each other.

•	to protect against tamper or fraud, documents must be protected from either accidental or intentional deletion or modification (i.e. restricted to read only access). Access to documents must be restricted to only those authorised by the Contractors’ Representative or the Superintendent. A register of persons so authorised is to be maintained by the Contractor and shall include a record of the written authorisation.

Documents must be accessible on-line within twelve (12) hours following the completion of the respective works.

The Contractor’s records management system shall include the provision of these documents by the Contractor to the Superintendent for review and acceptance prior to issue of a Certificate of Practical Completion. Within 7 days of the submission of each document, the Superintendent shall advise whether the document is accepted.

The Completed Works Report in the required Microsoft Excel format is available for download at:https://www.transport.tas.gov.au/roadworks/contractor_and_industry_information/specification_listings_-_standard_sections

The Completed Works Report shall also contain the following information:

•	records on the condition of the completed works (e.g. roughness surveys, deflection surveys, baselines for corrosion or other protection systems); and,

•	records relevant to assessing the structural capacity of the works, including, where applicable, sub-surface conditions, foundations and sub-structures.

The Contractor must provide an electronic copy of the design and construction records to the Principal prior to Final Completion in a format that will enable the records to be archived in the Principal’s Asset Management System

160.65	AS-CONSTRUCTED DRAWINGS

As-Constructed Drawings shall be prepared from the Principal supplied AutoCAD drawings (dwg) in accordance with State Growth Standard Specification T13 CADD Manual

A set of As-Constructed drawings in both AutoCAD drawing format (dwg) and Adobe Acrobat PDF format, generated from AutoCAD drawing files, shall be produced at a resolution suitable for effective interpretation.

Drawings shall be marked with the latest revision number and titled “As Constructed” on each drawing.  Any changed information on drawings is to be enclosed in a “revision cloud” for easy identification.

“As Constructed” information for installed and relocated services shall be included on the drawings and shall also be provided to each Service Authority with the relevant details and in the required formats to meet their individual requirements for this documentation.  Copies of this information with confirmation of receipt and acceptance by the Service Authority shall be supplied by the Contractor to the Superintendent.

For works requiring the design and construction or renewal of structures, the design calculations pertaining to the Issued for Construction design drawings will be supplied to the Superintendent.  This shall be completed by the Contractor prior to the Superintendent issuing the certificate for practical completion

160.66	SURVEILLANCE AND AUDITS BY THE SUPERINTENDENT

The Superintendent will arrange surveillance and audits to ensure that the Contractor is complying with the Quality Management System.

The Contractor shall, upon being given reasonable notice by the Superintendent, make or arrange to be available all facilities, documentation, records and personnel, including those of any sub-contractors, that are reasonably required for audits to be undertaken.

Notwithstanding that the Principal may have previously undertaken audits of a sub-contractor's quality management system in connection with other work, the Contractor shall include the operations of all such sub-contractors in the Contract quality plan and shall fulfil all the quality obligations of the Contract.

The Principal will carry out audit and surveillance of the work of all sub-contractors as it sees fit, in the same way that it may carry out audit and surveillance of all work done and materials supplied by the Contractor.  The Superintendent may for this purpose have recourse to audit and surveillance carried out for other contracts with the Principal.  Copies of any such audit and surveillance reports used by the Superintendent will be provided to the Contractor.

The Superintendent must be granted access to inspect and audit the contractor’s design and construction records and if requested by the Superintendent, the Contractor must arrange for personnel to explain the design and construction records.

The Superintendent must notify the Contractor at least 2 Business Day prior to an inspection specifying the scope of the records to be made available for audit.

160.67	NOT USED

160.68	CONTRACTOR’S SITE COMPOUND

The Contractor shall erect, maintain, secure and subsequently remove such buildings, compounds, sanitary accommodation, explosive magazines and associated services as required by the Contractor for the supervision and construction of the Works.  The Contractor shall obtain all necessary local municipal permits and approvals associated with the site establishment and access arrangements associated with its site compound.

The location and form of such buildings and compounds shall:

(a)	minimise noise, disturbance and inconvenience to all abutting properties

(b)	maintain a minimum clearance of 30 m to the closest boundary of all abutting properties

(c)	be consistent with, and complement the Environmental Management Plan and Health and Safety Co-ordination Plan

(d)	provide suitable hard-stand areas for storage of materials and equipment and parking vehicles

(e)	allow for all pedestrian traffic.

The Contractor, subject to the agreement of the Superintendent and the local municipal authority, may be permitted to use portions of the Site, for establishment of buildings and compounds.

The buildings, compounds, associated services, sanitary accommodation and explosive magazines erected by the Contractor shall be regarded as Materials or Construction Plant and as such shall be considered as Construction Plant under the l Conditions of Contract.

At the completion of the Works, these facilities will remain the property of the Contractor and shall be removed from the Site and the area reinstated to the satisfaction of the Superintendent.

160.69	NOT USED

160.70	WATER FOR CONSTRUCTION PURPOSES

The Contractor shall make its own arrangements for water supply to provide the quantity and quality required to complete the work.  For any chosen source of water supply, the Contractor shall obtain the necessary approvals from the appropriate authorities and shall act in accordance with any conditions stipulated.

160.71	NOT USED

160.72	PROGRAM

Within 20 Business Days after the Date of the Acceptance of Tender, the Contractor shall submit a Program to the Superintendent for review.

Further to the requirements of the Conditions of Contract, the Program must be computer based using ‘Microsoft Project 2007’ or an alternative computer program approved by the Superintendent.  It shall be in sufficient detail to demonstrate any entitlement that the Contractor may from time to time claim to have pursuant to the  Conditions of Contract and be capable of providing reports which are able to identify the following features in acceptable formats:

1.	detailed activities for all work elements including design activities, construction activities, service relocations and work by statutory authorities;

2.	procurement periods and delivery dates for major items of goods, plant and materials;

3.	activity dependencies;

4.	critical path activities identified for the Works and any Separable Portion of the Works;

5.	duration, earliest and latest start and finish dates and total and free floats for each activity;

6.	dates by which decisions or materials are required from the Superintendent or the Principal;

7.	milestones which identify significant events including completion of Separable Portions;

8.	allowance for adverse weather and other time risk allowances;

9.	non-work periods;

10.	dates by which design work or drawings to be produced by the Contractor or samples will be submitted to the Superintendent including allowance for reviews and re-submittals;

11.	the estimated value of work to be done each month throughout the Contract.

The Contractor shall submit with the Program the estimated contract value of work to be done each month throughout the Contract and detailed reasons for any divergence from the program and cash flow submitted with the tender.

- Utility Service Relocation

In developing the Program, the Contractor shall consider all issues associated with the relocation of public utility services.  The Contractor shall fully inform itself of the impact of the works under the Contract on existing services and make allowance in its Program for the lead times required by each service authority for design, liaison, supply of materials, notification to residents and construction periods, including making allowance for any periods of the year when services cannot be relocated.

The Contractor shall consider the impacts of its Service Relocation Strategy in the development of its Program.

(b)	Review of Program

(i)	If the Superintendent considers that the submitted Program or any subsequent revision thereto does not show sufficient details, or is impractical, or does not comply with the requirements of the Contract, or will not result in completion of the Works or any separable part of the Works by the relevant Date for Practical Completion, the Superintendent may direct the Contractor to resubmit to the Superintendent an amended Program within 5 business days for further review.

(ii)	Should the submitted construction program provide for completion of the Works or a separable part of the Works in advance of the relevant times for Practical Completion and the Superintendent does not direct the Contractor to supply an amended Program, the Contractor may proceed to prosecute the work in accordance with the submitted construction program at the Contractor's own risk.  The dates for particular activities or Practical Completion shown on a Program will not be accepted as a substitute for any corresponding specified dates in the Contract which shall continue to be the basis for assessment of progress of work and any claims made under the Contract for extensions of time and additional costs.

(c)      Updating and Reporting on Construction Program

The Contractor shall maintain a complete record of the Program, throughout the Contract.

(i)	The Contractor shall submit to the Superintendent an Updated Program:

1.	in accordance with the timing specified in the Conditions of Contract; or

2.	within 10 Business Days of any change to the critical path for the Works or any separable part of the Works.

3.	within 5 Business Days of a request to do so from the Superintendent including, if applicable, an explanation in writing of delays in execution of the WUC in comparison with the Program.

(ii)	The Updated Programs shall provide the same level of detail as the original Program and shall:

1.	show the ‘as-constructed’ program in respect of all work carried out to the time of updating;

2.	be accompanied by a statement of the reasons for any changes from the previously submitted Program;

3.	incorporate all extensions of time which have previously been granted or allowed up to that time by the Superintendent pursuant to the Conditions of Contract;

4.	be accompanied by a statement of any claims for extensions of time which have previously been notified by the Contractor in accordance with the Conditions of Contract in respect of which the Superintendent is yet to determine.

(iii)	Any Updated Program submitted in accordance with (i) above shall be reviewed by the Superintendent on the basis set out in item (c) above.

(d)	Rate of Progress

Where the Superintendent at any time considers that the rate of progress is insufficient to ensure completion of the Works or any separable part of the Works by the relevant Date for Practical Completion, the Superintendent may direct the Contractor to submit within 10 Business Days written details of the intended procedure for the execution of the remainder of the WUC.

160.73   SITE MANAGEMENT AND SUPERVISION   ##(strikethrough inapplicable requirements below):

(a)	 Site Supervision

The Contractor's site management, programming and program control, quality assurance and methods of work shall be supervised daily by an experienced and qualified engineer.  This engineer shall possess the experience and qualifications which would be acceptable to the Institution of Engineers Australia as satisfying the requirements for Corporate Membership, including at least 5 years experience in the relevant construction field.

(b)    Site Survey

For the purposes of setting out the Works in conformity with the specification and drawings, the Contractor shall engage an experienced and qualified surveyor.  This surveyor shall possess the experience and qualifications which would be acceptable to the Institution of Surveyors, Australia as satisfying the requirements for Corporate or Associate Membership or alternatively, possess the experience and qualifications which would be acceptable for Membership to the Institution of Engineering and Mining Surveyors, Australia.

The surfaces and quantities measured by the Contractor under this Contract shall be made available to the Superintendent in an electronic format or other format approved by the Superintendent.

(c)	Landscape Supervisor

The Contractor shall nominate a Landscape Supervisor to be on site for the duration of all landscape work.  This person shall have a Landscape Trade Certificate (TAFE), equivalent qualification or at least 2 years horticultural expertise on work of a similar size and scope.

Should the Contractor's site supervisory staff prove unsatisfactory with respect to progress, quality of work and methods of work, the Superintendent may direct the Contractor to provide such additional competent and experienced staff as may be necessary to ensure satisfactory progress of the Works and that the quality and the methods of work are acceptable.

160.74	NOT USED

160.75	NOT USED

160.76	EXAMINATION AND TESTING OF MATERIALS AND WORK

(a)	General

The Contractor shall be responsible for carrying out all examination and testing of materials and WUC in accordance with the requirements of the specification.

Unless otherwise specified, materials and workmanship shall comply with the relevant standard as defined in Section 175.

(b)	Allowance for Testing in Construction Program

The Contractor shall make allowance in the construction program for the time necessary to arrange for and to carry out examination and testing of materials and work.

(c)	Notification

Where inspection of materials or work by the Superintendent or his representative is specified as a hold point, or where a hold point is created by a nonconformance, at least 24 hours notice of testing and/or inspection shall be given to the Superintendent.

(d)	Tests

Unless otherwise specified, all tests and sampling shall be undertaken in accordance with the appropriate VicRoads codes of practice and applicable test methods as current at the time of performance of the tests.  Unless otherwise specified, all tests shall be conducted by experienced testing officers in a laboratory accredited by the National Association of Testing Authorities (NATA) for the test methods used under the Contract and all tests shall be endorsed in accordance with the NATA registration for that laboratory.

Lists of current VicRoads codes of practice are available online at the VicRoads website www.vicroads.vic.gov.au.

All construction materials sampling shall be undertaken by either:

(i)	personnel from a NATA laboratory accredited for the appropriate sampling methods; or

(ii)	personnel who have successfully completed an accredited TAFE course in sampling of construction materials delivered by a registered training organisation, and have taken a refresher course in sampling of construction materials every three years.

The sampler shall be identified on the test report.

(e)	Test Results

The Contractor shall submit to the Superintendent a monthly summary, or if requested by the Superintendent a weekly summary, of testing undertaken.  The summary shall include details of all tests undertaken, the result of each test and sufficient additional information to demonstrate that the specified minimum frequency of testing is being complied with.

The summary of test results shall be submitted to the Superintendent by the second day of the week following the relevant period.

(f)	Calibration

All test equipment used for tests, carried out in accordance with Clause 160.76(d) above, shall be calibrated by a laboratory accredited by NATA for the particular calibration method.

160.77	DRAINAGE OF WORK SITE

The Contractor shall at all times provide for the safe discharge of seepage, drainage and stormwater during the execution of the works under the Contract.  The Contractor shall be responsible to obtain all approvals from the local authorities and accept all costs associated with the discharge of any water into an existing outfall on a temporary or permanent basis.

160.78	NOT USED

160.79   INSTRUCTIONS BY OTHER GOVERNMENT DEPARTMENTS AND AUTHORITIES

Other government departments and authorities and their representatives, whether federal, state or local, often have responsibilities that impact on Department of State Growth’s works.

The Contractor shall report any instruction (orders or directions) given by an authorised representative of these government departments and authorities to the Superintendent immediately by mobile phone or as soon as practicably possible.

The Contractor shall co-operate with an authorised representative who is requesting access to the site under powers conferred by legislation and follow any instructions given by the authorised representative in the format nominated by the legislation.

160.80	INSPECTION OF PROPERTY

Prior to commencing operations, the Contractor shall engage a suitably qualified and experienced Building Surveyor to undertake inspections on all buildings and structures (including heritage structures) within a minimum distance of 100 m for general construction works and 200m of any blasting. Two copies of the written existing conditions report for each property, including any photographs, shall be prepared and signed by the property owner.

The condition of the buildings, structures and the property shall be detailed in the existing conditions reports which shall form the basis of assessment of any structural damage to buildings and structures arising out of the Contractor’s operations in the event of a claim by the owner/occupier.  The Contractor shall be responsible for the repair of any damage caused to property due to the Contractor’s operations.

The Contractor shall submit to the Superintendent a copy of all existing condition reports of property and buildings prior to commencing work adjacent to such property or building.

For the purposes of this clause the Site is defined as the nearest point of the work adjacent to any building or structure.

The Contractor shall bear all costs associated with any claim for damages resulting from the effects of the Contractor’s operations, including ground vibration, directly caused by the Contractor's construction methods.  The cost of such damage shall be in addition to damage caused by other action attributed to the Contractor's work.

Before final payment is made, the Contractor shall obtain written clearance from all landowners and occupiers affected by the provision of this clause, to certify that the landowner and occupier have no claim for any loss or damage due to the Contractor’s operation.  A copy of all written clearances shall be forwarded to the Superintendent prior to the Contractor’s Final Claim.

160.81	WORK IN PRIVATE PROPERTY

Where the Contractor is authorised by the Superintendent to enter private property to carry out WUC, the Contractor shall give the owner and occupier of the land a minimum of 5 Business Days notice of intention to enter or to remove any fence and shall also erect any temporary fencing that may be necessary.

Entry shall be by a gate, or gates to be erected by the Contractor which shall be kept securely locked when not in use.  Where fences are rabbit proof, the gates erected shall also be made and kept rabbit proof, and the Contractor shall be responsible and liable for the trespass of vermin.

160.82	CLEARANCES FROM LANDOWNERS AND OCCUPIERS

Before final payment is made, the Contractor shall produce written clearances from all owners and occupiers whose properties have been entered by the Contractor or the Contractor's employees or agents, for the purpose of carrying out WUC.

160.83	USE AND CARE OF ROADS

The Contractor shall be responsible for repair of damage caused to any roads, bridges or other structures by transporting material under the Contract.  The Contractor is advised that the Department of State Growth and municipal councils have power under their respective Acts to recover the cost of repair of damage to roads.  If requested by the Superintendent, the Contractor shall submit clearances from municipal and other authorities concerned before the Final Certificate is issued.  In respect of repair of damage to roads, the Contractor will be deemed when tendering:

- to have inspected the roads used for transport and prepared and submitted a report to the Superintendent, describing the condition of these roads prior to transporting material under the Contract upon said roads;

  - the report may include video or photographs to explain the nature and location of the road condition features.

(b)	to have acquired, by consultation with the municipal or other authorities concerned, knowledge of the roads and any existing or likely restrictions upon their use which could affect the transport proposals;

(c)	to have assessed the possibility and extent of any damage to the roads which may be caused by transport under the Contract;

(d)	to have made due allowance for the effects of such restrictions and for the cost of rectification of such damage in accordance with the requirements of the authorities concerned.

160.84	INCIDENT REPORTING

This Clause and the following Clauses 160.85 and 160.86 do not apply to Work Health and Safety incidents.

The Contractor shall implement and maintain an Incident Reporting System for the duration of the Contract. The Contractor shall enter, into the Incident Reporting System, details of all incidents (including ‘near incidents’ also commonly, but incorrectly known as ‘near misses’ ) arising from or relating to the WUC, or on or adjacent to the site, during the Contract term, which may, or could, have resulted in claims for personal injury or property damage to third parties.

The Incident Reporting System shall record all incidents in respect of which any third party may claim. This shall include any possible claim for personal injury and all damage to property.

The Incident Reporting System shall also record details of notes, records and photographs or any other evidence relating to any incident.

The Incident Reporting System shall also record details of any injury or damage caused by registered motor vehicles.

160.85	ACTIONS IN RESPECT OF INCIDENTS

The Contractor shall take immediate steps to minimise the extent of personal injury or property damage arising from an Incident. The Contractor shall take careful note of the evidence surrounding the Incident, including notes or reports of the facts relating thereto and photographs.

The Contractor shall, as soon as practicable, inform the Principal in writing of any Incident that may give rise to a claim under an insurance policy effected as required by any of the insurance clauses under the Conditions of Contract and shall ensure that the Superintendent is kept fully informed of the Incident, the subsequent action and developments concerning the claim.

The Contractor shall take such steps as are necessary or appropriate to ensure that a sub-contractor shall, in respect to an event or claim of a like nature arising out of or relating to the operations or responsibilities of the sub-contractor, take in relation to the Superintendent the like action to that which the Contractor is required to take under this clause.

Where the Incident is reportable to the Principal’s Insurer under its Policy, the Contractor shall, in accordance with Policy conditions:

(a)	notify the Principal’s Insurer immediately -

(1)	by telephone if the matter is sufficiently serious to alert the Principal’s Insurer and seek advice

(2)	in writing, with a copy to the Superintendent

and preserve any evidence, such as notes or photographs;

(b)	send to the Principal’s Insurer immediately upon receipt any letter of demand, writ, claim, summons or proceedings or other like documentation;

(c)	co-operate with the Principal’s Insurer in the investigation and defence of claims, including attendance at court if required.

All claims or correspondence received from third parties relating to incidents arising from or relating to the WUC, which does, may, could result or may have resulted in a third-party claim shall be actioned as follows;

- Within 3 days of receipt of the claim or correspondence, respond directly to the third-party acknowledging receipt of the claim or correspondence and where applicable provide details of the insurance process and timeframes for investigating the matter.

- Whilst the matter is under investigation, each and every subsequent 21 days since last responding to the claim or correspondence, respond directly to the third-party to report on the progress with investigations.

- Once investigations have concluded and any claim determined, respond directly to the third party detailing the reasons for rejection or acceptance of a claim.

160.86	MONTHLY REPORTING

The Contractor shall report monthly to the Superintendent on all incidents included in the Incident Reporting System, including details of which matters have been reported to the Principal’s Insurer (together with the date of such report) and the status of resolution of each Incident.

160.87	AUDITING OF INCIDENT REPORTING SYSTEM

The Contractor shall permit the Superintendent, staff of the Principal’s Insurer, its auditors or any other auditors approved by the Superintendent to access and audit the Incident Reporting System and any documentation associated with claims or relating to Incidents or near Incidents and to take copies of any documents associated with claims or relating to the Incidents.

160.88	Work Health and Safety INCIDENT REPORTING

Pursuant to clause 11B.6 (v) of the Conditions of Contract the Contractor shall undertake incident reporting in accordance with the Conditions of Contract through the State Roads’ nominated Contractor Work Health and Safety incident management software.

The Principal will provide the Contractor with up to 5 accounts under the Contract (for Site Supervisor, WHS Advisor and any others requested). To enable this access to be provided the Contractor shall provide the following information, for each user, prior to commencing work on site.

- Full name

- E-mail address

- Phone number

Following receipt of this information the Principal will provide login details and any familiarisation training required.

160.89	USE OF HEAVY VEHICLE TRAILERS AT WORKSITES

This applies to the following heavy vehicle dog trailers used to run out material delivered to sites under contract with the Principal:

- Quad (four axle) dog trailers

- Quin (five axle) dog trailers

Materials relevant to this Specification relates to all materials which are run-out on-site and not stockpiled materials.

## Requirements

## Responsibilities

The following are the responsibility of the head contractor:

- Manage sub-contractor compliance with above and below requirements

- Ensure the safe delivery of materials to all worksites including the undertaking of pre-delivery risk assessments to consider issues such as – wind, ground conditions, centre of gravity of load, load type, trailer physical characteristics and experience of driver.

- Ensure that all drivers are trained and verified as competent to perform the tipping task.

- Undertake a risk assessment when material is to be unloaded within 10m of live traffic. This shall include an assessment of suitable traffic management controls.

- Monitor and document compliance through regular audits.

- Equipment

- Heavy vehicle quad dog and quin dog trailer trays must have a Teflon lined floor, or an alternative material that meets or exceeds the performance standards of Teflon, to perform the tipping task when running out material.

- Any proposed alternative materials must be approved by the Principal prior to use on State Roads worksites.

- Heavy vehicle trailers without approved controls can only be used for stockpiling on worksites.

- Heavy vehicle semi-trailer tippers must not be used to run out material with a lifted tray under any circumstances.

- Heavy vehicle semi-trailer tippers can be used as a side tipper or for stockpiling of material when normal risk assessment processes are followed by the contractor.

## Technology

- All future engineering control technologies developed for market use to minimise the likelihood of trailer rollover not specified above must be approved by the Principal prior to their use under this or any other State Roads contract.

- Applications for alternative technologies or materials must be submitted to  the Superintendent for consideration by the Principal at least 10 days prior to intended use on site.

| Ed/Rev Number | Clause Number | Description of Revision |
| --- | --- | --- |
| May 2019 | All | New document to include project specific clauses replaces previous Section 160- Construction-General and Project Specific Clauses |
| April 2020 | 160.02 160.09 A,B & C 160.16 160.49A 160.64 160.85 160.91 160.92 | Additional items added Clause numbering corrected New clause New clause Updated records requirements Clause removed now in new Section 177 New clause New clause |
| August 2020 | 160.41D | New clause |
| October 2020 | 160.41 160.07 | Removed Added detail from 160.41 |
| November 2020 | 160.88 | Added new paragraph on third party claims |
| May 2021 | 160.03 160.13 160.42 160.45 160.46 160.49A 160.53 160.65 160.67 160.69 160.71 160.74 160.75 160.80A and 160.80B 160.88 | Added clause to ensure Contractor provides regular cash flow forecast to Superintendent Amended wording Removed all of 160.42, 160.42a, 160.42b, 160.42c as this is to be transferred into Section 176 Removed entire clause as it is a repeat of 160.14 Removed entire clause as it is a repeat of 160.15 Move clause to be included in 160.11 Adding of drafting note to cover project specific hold points being added to the contract. Amended wording Removed entire clause Removed entire clause Clause moved to 160.10 Removed entire clause Removed entire clause Moved to incorporate into 16012A, 160.12B, 160.12C Removed both references to "... at its own expense..." for the Contractor. Included claim for damages clauses that had previously been removed |
| August 2023 | 160.02 160.07 160.07 (roadworks roundup) 160.07 160.10 160.53 160.80, 160.80A, 160.80B 160.80 and beyond 160.81 160.92 | Revised requirements for management of SCEP process Updated traffic management detail to capture missing detail following withdrawal of 167 and include relevant hold points Revised entire clause Added property access previously captured in 160.81 Changes to wording in a), b) & c) Inclusion of additional Superintendent hold points Removed as already covered in 160.12 Changes to clause numbering due to removal of clauses Moved to within 160.07 (traffic management) Updated to 160.89 Revised entire clause |
| June 2024 | 160.01 160.02 160.03 160.04 160.06 160.07 160.08 160.09C 160.10 160.41 160.53 160.72 160.78 160.84 | Updated reference to AS4000-1997. Contract Management Plan requirements updated to align with defined terms and requirements in AS4000-1997 and relevant preconditions applicable to Contractor detailed to align with requirements in AS4000-1997 Program requirements consolidated. Removal of section as Conditions of Contract now triggers application of Section 199. Removal of Scope of Work and Link/Chainage reference as now captured in the Conditions of Contract. Updated Roadworks Roundup website link. Statutory Requirements/Approvals are removed since these details are now included in the Conditions of Contract. Minor edits to include ‘Faunal Habitats’ in the table. Updated to include review and approval process for Project Information Signs as Superintendent Hold Point. New clause inserted to include review and approval process for signage as Superintendent Hold Point. Hold Point at 160.02 removed and a new Superintendent Hold Point is inserted to reflect the new requirements of Section 160.41. Program requirements are updated to align with AS4000-1999 and remove reference to minor works program. Removed in its entirety. Minor amendment to update incorrect clause referencing. |

# Text boxes

HP 	the Traffic Guidance Schemes shall be submitted to the Superintendent not less than 4 working days prior to implementation of the proposed traffic arrangement.

HP 	An amended Traffic Guidance Scheme shall be submitted to the Superintendent not less than 4 working days prior to implementation of the proposed traffic arrangement.